## Slide 1
DELIVERY REVIEW
Evergreen Insurance Quote
DELIVERY GOAL
By Thursday EOD, an assembled, themed, responsive Evergreen Quote app with the wired quote calculator is merged to main via reviewed PR with a green CI run.
✓ GOAL HIT
All 5 "Done" criteria met
— App on main — themed & responsive
— Calculate Premium returns a real number
— Green CI run on merge commit
— Reviewed PR merged, branch deleted
— delivery-leadership-package/ committed
Shadd Schutte · Delivery Lead · July 2026
Notes: Delivery goal from delivery-goal.md. All five Done criteria confirmed. Early decisions — legal hold on testimonials, scope protection on Compare Plans — prevented any blockers from becoming critical.

## Slide 2
Evergreen Insurance Quote — Delivery Review
2
WHAT SHIPPED
Evergreen Quote v1.0 — delivered to main
🌿
Assembled HTML
index.html — 5 sections: nav, hero, quote form, testimonials placeholder, footer
🎨
Brand Theme
css/theme.css — Evergreen green palette, Bootstrap 5.3.2, mobile-first responsive
🧮
Quote Calculator Wired
js/quote-calc.js — calculatePremium() live for auto, home, renters, condo
🔁
CI Workflow Enabled
.github/workflows/ci.yml — HTML check, required-files check, JS syntax lint
📋
Leadership Package
delivery-goal, risk-register, decision-memo, status-update committed to repo
📷 App main| 🔗 PR link | ✅ CI run link
Notes: Walk each row. Pause on CI — that is the objective evidence. Point to the screenshot placeholder and paste your actual PR + CI URLs here before presenting.

## Slide 3
Evergreen Insurance Quote — Delivery Review
3
TWO KEY DECISIONS
Calls that protected delivery & compliance
01
Comment out testimonials; ship "Coming Soon" placeholder
Why it mattered
Legal hold on all three customer quotes — shipping them risked a compliance violation that could have pulled the entire release.
Trade-off
Slightly less content on launch day vs. zero compliance risk and a clean, professional placeholder.
Reversibility
One code change (uncomment + remove placeholder) the moment signed releases arrive — no rebuild required.
02
Time-box "Compare Plans" nav link to 30 minutes max
Why it mattered
Marketing's A/B test request arrived mid-sprint and threatened to push Day 3 script wiring — the core deliverable.
Trade-off
Accommodate only if it fit in a single <li> addition with a confirmed destination URL by Wednesday EOD.
Outcome
Scope boundary held. Quote calculator wired on schedule. Request logged as R2 in risk register.
Notes: Both decisions are documented in decision-memo.md. The key theme: both were compliance and scope protection calls made proactively, not reactive firefighting.

## Slide 4
Evergreen Insurance Quote — Delivery Review
4
RISKS & INJECTS
Tracked, managed, and closed
TOP RISK TRACKED
R3 — theme.css vs Bootstrap 5 mobile conflict (Likelihood: M · Impact: H)
Mitigation: Tested at 375px, 768px, and 1280px after every section assembly; Bootstrap CDN pinned at 5.3.2. Status: No layout breakage on any breakpoint — RISK CLOSED.
Sprint Injects
TUE Inject #1
Legal hold on customer testimonials
Legal informed the team that signed release forms were required — a ~2-week process. Re-prioritized immediately: commented out the testimonials section, inserted "Coming Soon" placeholder, and documented the decision in decision-memo.md. No delivery work lost.
WED Inject #2
Marketing requests "Compare Plans" nav link by Thursday
Mid-sprint scope request to support an A/B test. Assessed against delivery goal: wiring the quote calculator was the core Day 3 commitment. Time-boxed to 30 min only with confirmed URL by Wednesday EOD. Logged as R2. Go/No-Go: GO — CI green, core deliverables intact.
Notes: R3 was the highest-impact risk in the register. Both injects were handled without missing the delivery goal. The Go/No-Go call was straightforward — CI was green and core work was intact.

## Slide 5
Evergreen Insurance Quote — Delivery Review
5
WHAT I'D DO DIFFERENTLY
Retrospective — next round improvements
1
Confirm legal review window at kick-off, not Day 2
The testimonials hold landed as an inject, but the question could have been surfaced in Day 1 planning. One intake question — 'Is any content pending legal or brand approval?' — moves this from inject to known constraint.
→ Add a legal/brand approval gate question to the project kick-off checklist.
2
Require destination URL before accepting nav requests
The 'Compare Plans' request arrived without a destination URL, making it effectively unexecutable. Accepting scope items without their dependencies creates register items that can't be closed.
→ New feature requests must include a destination URL, acceptance criteria, and a named owner before entering scope.
3
Run premium output sanity-check before form wiring
The brief flagged placeholder rate values as a known risk. A 5-minute spot check of calculatePremium() edge cases on Day 3 before form wiring would have closed R4 faster and surfaced any odd-looking numbers before demo.
→ Add an output-range check step to the Day 3 script wiring task — costs under 10 minutes.
Q&A: "Why didn't you ship testimonials?" · "With 3 engineers, first ask: who owns legal comms?"
Notes: Frame these as growth, not failure — all three improve an already-successful sprint. Q&A prep strip is speaker context for rehearsal.